## Roles
Roles
Each person owns a clear area. Everyone tests, joins the demo, and helps with the deck.
Owner | Area
Chavi | Agent core - the agent loop, LLM tool-calling, the 6-component system prompt, and integration. Adds the error-handling bonus.
Tzvia | Tools & data - the two tools (nearby places + route ordering), the places-API setup, and input validation.
Efrat | App & docs - the Streamlit interface (address, interest buttons, itinerary, map), the documentation and reflection write-up, and the slide deck.

## Milestones
Key Milestones
Deadlines pulled to Thu/Fri so Friday evenings and Saturdays stay clear.
Date | Milestone | Gate (must be true)
Mon Jun 22 | Contracts frozen | Tool signatures + Place schema locked -> parallel work starts
Fri Jun 26 (day) | MVP happy path works | Address + interests -> ordered tour on a map, 3x; before Shabbat
Sun Jun 28 | Teacher checkpoint | Live demo + questions answered; feedback captured as tasks
Thu Jul 2 | Code freeze + hardening done | Error handling in; edge cases tested; docs drafted; code frozen
Fri Jul 3 (day) | Deck + rehearsal done | Deck final, backup video recorded, rehearsed; before Shabbat
Sun Jul 5 | Submit | Deliverables checklist 100% complete (buffer day)

## Tasks
Walking-Tour Guide Agent ¦ Task Tracker
No work Friday evening or Saturday (Shabbat). Friday daytimes (Jun 26, Jul 3) are the main build blocks. Checkpoint Sun Jun 28; due Sun Jul 5.
Phase | Task | Owner | Start | Due | Status | Notes
0 - Setup (Jun 21-22) | Create repo, shared doc, API keys + decide the places API | Chavi | Jun 21 (Sun) | Jun 22 (Mon) | Not Started | Pick a free, low-friction API
0 - Setup (Jun 21-22) | Freeze tool signatures + Place schema (contracts.py v1) | Chavi | Jun 22 (Mon) | Jun 22 (Mon) | Not Started | Most important step - unblocks parallel work
0 - Setup (Jun 21-22) | Get geocoding working + confirm API returns good results | Tzvia | Jun 22 (Mon) | Jun 23 (Tue) | Not Started | Address -> lat/lng; test a few real spots
0 - Setup (Jun 21-22) | Agree the one demo scenario (address + interests + time) | All | Jun 22 (Mon) | Jun 22 (Mon) | Not Started | Shared target to build toward
1 - Core MVP (Jun 23-26) | Agent loop + LLM tool-calling (stub tools) | Chavi | Jun 23 (Tue) | Jun 24 (Wed) | Not Started | The brain - core milestone
1 - Core MVP (Jun 23-26) | Draft the 6-component system prompt | Chavi | Jun 24 (Wed) | Jun 25 (Thu) | Not Started | Most of the quality lives here
1 - Core MVP (Jun 23-26) | Add logging of tool calls + decisions | Chavi | Jun 25 (Thu) | Jun 25 (Thu) | Not Started | Feeds the reflection / Solutions slide
1 - Core MVP (Jun 23-26) | Build get_nearby_places (geocode + places API) | Tzvia | Jun 23 (Tue) | Jun 25 (Thu) | Not Started | Interest buttons -> real places
1 - Core MVP (Jun 23-26) | Build order_walking_route (nearest-next) | Tzvia | Jun 24 (Wed) | Jun 25 (Thu) | Not Started | Makes the list an actual walk
1 - Core MVP (Jun 23-26) | Test the tools on 3 sample scenarios | Tzvia | Jun 25 (Thu) | Jun 25 (Thu) | Not Started | Catch bad data early
1 - Core MVP (Jun 23-26) | Streamlit UI: address line + interest buttons -> itinerary | Efrat | Jun 23 (Tue) | Jun 25 (Thu) | Not Started | What the user actually touches
1 - Core MVP (Jun 23-26) | Simple route map display | Efrat | Jun 25 (Thu) | Jun 25 (Thu) | Not Started | The demo 'wow'
1 - Core MVP (Jun 23-26) | Integration: wire the end-to-end happy path | All | Jun 26 (Fri) | Jun 26 (Fri) | Not Started | Main all-hands block - DAYTIME, wrap before Shabbat
1 - Core MVP (Jun 23-26) | Dry-run the demo x3 | All | Jun 26 (Fri) | Jun 26 (Fri) | Not Started | Daytime - must work 3x in a row
** Sat Jun 27 - OFF (Shabbat) ** | No work | All | Jun 27 (Sat) | Jun 27 (Sat)
CHECKPOINT - Jun 28 (Sun) | Teacher session: demo + collect feedback/questions | All | Jun 28 (Sun) | Jun 28 (Sun) | Not Started | Bring a WORKING happy path
2 - Harden (Jun 29-Jul 2) | Incorporate teacher feedback (priorities first) | All | Jun 29 (Mon) | Jun 30 (Tue) | Not Started | 30-min re-plan right after checkpoint
2 - Harden (Jun 29-Jul 2) | Error-handling bonus: no results / bad address / API fail | Chavi | Jun 30 (Tue) | Jul 1 (Wed) | Not Started | The chosen bonus
2 - Harden (Jun 29-Jul 2) | Tighten the system prompt + test edge cases | Chavi | Jul 1 (Wed) | Jul 2 (Thu) | Not Started | Fixes most 'inconsistent' issues
2 - Harden (Jun 29-Jul 2) | Input validation (address present? interests chosen?) | Tzvia | Jun 30 (Tue) | Jul 1 (Wed) | Not Started | Stops garbage requests
2 - Harden (Jun 29-Jul 2) | Draft the documentation (does / works / doesn't) | Efrat | Jun 29 (Mon) | Jul 1 (Wed) | Not Started | Be honest about limits
2 - Harden (Jun 29-Jul 2) | Draft reflection answers + start the deck | Efrat | Jul 1 (Wed) | Jul 2 (Thu) | Not Started | Pulled early - Friday is short
2 - Harden (Jun 29-Jul 2) | Bug-bash: try to break each other's parts | All | Jul 2 (Thu) | Jul 2 (Thu) | Not Started | Fresh eyes find bugs
2 - Harden (Jun 29-Jul 2) | Code freeze + final end-to-end test | All | Jul 2 (Thu) | Jul 2 (Thu) | Not Started | Freeze Thu so Friday is just polish
3 - Polish & Deck (Fri Jul 3) | Finalize the deck + record a backup demo video | Efrat | Jul 3 (Fri) | Jul 3 (Fri) | Not Started | Daytime - whole team reviews; video = insurance
3 - Polish & Deck (Fri Jul 3) | Rehearse the presentation | All | Jul 3 (Fri) | Jul 3 (Fri) | Not Started | Daytime - wrap before Shabbat
** Sat Jul 4 - OFF (Shabbat) ** | No work | All | Jul 4 (Sat) | Jul 4 (Sat)
SUBMIT - Jul 5 (Sun) | Final deliverables-checklist pass + submit | All | Jul 5 (Sun) | Jul 5 (Sun) | Not Started | Buffer day - code already frozen